## Project Planner
Project Planner
[5 empty] | Current Day | 15 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Initial research about topic before first meeting | 1 | 2 | 1 | 2 | 100%
Clarify project aims and goals | 2 | 1 | 2 | 1 | 100%
Prioritise project goals | 2 | 1 | 2 | 1 | 100%
Define project requirements | 2 | 1 | 2 | 1 | 100%
High level design of license plate recognition | 5 | 5 | 8 | 8 | 50%
High level design of P2P network | 15 | 5 | 15 |  | 0%
High level design of security issues, encryption | 30 | 5 |  |  | 0%
Coding of license plate recognition | 5 | 10 | 8 |  | 30%
Coding of P2P network | 20 | 10 |  |  | 0%
Coding of privacy issues, encryption | 35 | 10 |  |  | 0%
Testing of license plate recognition | 20 | 5 | 15 |  | 15%
Testing of P2P network | 30 | 5 |  |  | 0%
Testing of privacy issues, encryption | 45 | 5 |  |  | 0%
Integration of all systems, along with possible hardware | 50 | 10 |  |  | 0%
Packaging and release on GitHub | 50 | 2 |  |  | 10%
Documentation of code | 50 | 2 |  |  | 10%
Report writing | 50 | 10 |  |  | 0%
Making of demo | 55 | 5 |  |  | 0%